## Team
Initials | First | Last | Email | GitHub Username | ScrumMaster
pc | Prateek Singh | Chauhan | pchauha2@stevens.edu | sabudanakichdi | Yes
mm | Monica | Mallamputti | mmallamp@stevens.edu | Monicaprojects21 | No
vm | Vishnu | Mandula | vmandula@stevens.edu | Vishnu1604 | No
ds | Diya | Sanghvi | dsanghv1@stevens.edu | Diya1201 | No
vs | Vikas Singh | Vyaqti | vsingh22@stevens.edu | VyaqtiVikasSingh | No
|  |  | GitHub Repository: | https://github.com/sabudanakichdi/ssw555_agile_project

## Backlog
Sprint | Story ID | Story Name | Owner | Status
| EPIC-1 | Project Planning and Set Objectives and Design flow
1 | S5-1 | Develop a Project Plan | pc | Done
| EPIC-2 | Requirement Analysis
1 | S5-12 | Requirement and Fuctionality Analysis for Sales Module | vs | Done
1 | S5-13 | Requirement and Fuctionality Analysis for Construction Module | vv | Done
1 | S5-14 | Requirement and Fuctionality Analysis for Operation Module | mm | Done
1 | S5-15 | Requirement and Fuctionality Analysis for End-Customer Module | ds | Done
3 | S5-16 | Requirement and Fuctionality Analysis for Rule Engine | pc | To Do
| EPIC-4 | Database Config and Integration
1 | S5-36 | Create and Configure Database connection | pc | Done
1 | S5-37 | Database Hosting in AWS | pc | Done
2 | S5-38 | Create Database design | pc | To Do
2 | S5-39 | Create Database Schema and tables | pc | To Do
| EPIC-3 | Sales Service API
1 | S5-50 | Sales: Create REST API Framework using Swagger | ds | Done
1 | S5-59 | Sales UI Design and project Setup | mm | Done
1 | S5-61 | Sales: Onboarding Customer - Page 1 | vv | Done
1 | S5-65 | Sales: Set Dependencies and initial project setup | ds | Done
2 | S5-63 | Sales: Onboarding Customer Page -2 | vv | To Do
2 | S5-64 | Sales: Agreement View Page | mm | To Do
2 | S5-29 | Sales: Customer onboarding API | ds | To Do
2 | S5-69 | Sales: Agreement view API | vs | To Do
| EPIC-3 | End Customer Service API |  | To Do
3 | S5-16 | End-Customer: Create REST API Framework using Swagger | pc | To Do
| EPIC-4 | DevOps Server Configuration
2 | S5-77 | Configure Jenkins/AWS CI/CD | pc | To Do
| S5-79 | Setup AWS EC2 instance for Sales Service | pc | To Do

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2022-06-06 | 24 |  | 0
Sprint 1 | 2022-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2022-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2022-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2022-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2022-02-23 | 28 |  | 0
2023-03-07 | 17 | 11 | 149 | 120 | 74.5

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time (In hours) | Act Size | Act Time | Completed
EPIC-1 | Project Planning and Set Objectives and Design flow
S5-1 | Develop a Project Plan | pc | Done | 0 | 8 | 5 | 7 | 2023-02-23
S5-2 | Identify and understand the problem statement for given solar management tool | pc | Done
S5-4 | Identify and understand the problem statement for given solar management tool | ds | Done
S5-5 | Identify and understand the problem statement for given solar management tool | vs | Done
S5-6 | Identify and understand the problem statement for given solar management tool | mm | Done
S5-7 | Identify and understand the problem statement for given solar management tool | vv | Done
EPIC-2 | Requirement Analysis
S5-8 | Requirement and Fuctionality Analysis for Sales Module | vs | Done | 0 | 8 |  |  | 2023-02-25
S5-10 | Identify the key features and functionalities | vs | Done
S5-11 | Identity the specific data and analytics required for dashboard | vs | Done
S5-12 | Create a Requirement analysis report | vs | Done
Done
S5-13 | Requirement and Fuctionality Analysis for Contruction Module | vv | Done | 0 | 8
S5-17 | Identify the key features and functionalities | vv | Done
S5-21 | Identity the specific data and analytics required for dashboard | vv | Done
S5-25 | Create a Requirement analysis report | vv | Done
Done
S5-14 | Requirement and Fuctionality Analysis for Operations Module | mm | Done | 0 | 8 | 2 | 8 | 2023-02-28
S5-18 | Identify the key features and functionalities | mm | Done
S5-22 | Identity the specific data and analytics required for dashboard | mm | Done
S5-26 | Create a Requirement analysis report | mm | Done
Done
S5-15 | Requirement and Fuctionality Analysis for End-User Module | ds | Done | 0 | 8 |  |  | 2023-02-28
S5-19 | Identify the key features and functionalities | ds | Done
S5-23 | Identity the specific data and analytics required for dashboard | ds | Done
S5-27 | Create a Requirement analysis report | ds | Done
EPIC-4 | Database Config and Integration
S5-36 | Create and Configure Database connection | pc | Done | 0 | 4 |  |  | 2023-03-01
S5-41 | Choose a database management system (DBMS) that suits your project's requirements, such as MySQL, PostgreSQL, or MongoDB. | pc | Done
S5-42 | Install the database software on your server or local machine. | pc | Done
S5-37 | Database Hosting in AWS | pc | Done | 0 | 8 |  |  | 2023-03-05
S5-43 | Choose a cloud service provider and Create a new virtual machine instance and assign it resources like CPU, memory, and storage. | pc | Done
S5-44 | Install the database software on the virtual machine and create a new database instance and assign a name to it. | pc | Done
S5-45 | Create a new user account for the database with appropriate privileges. | pc | Done
S5-46 | Open the necessary network ports to allow external access to the database. | pc | Done
EPIC-3 | Sales Service API
S5-50 | Sales: Create REST API Framework using Swagger | ds | Done | 20 | 16 | 25 | 8 | 2023-03-01
S5-53 | Sales Agreement view API | ds | Done
S5-55 | Sales agreement Confirmation API | vv | Done
S5-54 | Sales Agreement Generate API | mm | Done
S5-52 | Sales Customer Onboarding API | vs | Done
S5-59 | Sales UI Design and project Setup | mm | Done | 50 | 16 | 45 | 16 | 2023-03-07
S5-84 | Angular Project Structure | mm | Done
S5-85 | Sales UI Design | mm | Done
S5-61 | Sales: Onboarding Customer - Page 1 | vv | Done | 50 | 16 | 45 | 16 | 2023-03-07
S5-86 | Angular Project Setup | vv | Done
S5-87 | Sales: Onboarding Customer - Page 1 | vv | Done
S5-88 | Dev Test: Onboarding Customer - Page 1 | vv | Done
S5-65 | Sales: Set Dependencies and initial project setup | ds | Done | 30 | 16 | 27 | 16 | 2023-03-07
S5-67 | Set project frame Structure | ds | Done
S5-66 | Setup dependencies using Maven | vs | Done
|  |  |  | 150 | 116 | 149 | 71
Review Results
| Sprint Progress | 100% | Complete
| Done | 100%
| In Progress | 0%
| To Do | 0%
Standup Review (03/07):
Successfully Demonstrated the service project setup and UI project setup
Discussed the functionality covered for both API and UI.
Sales Customer Onboarding API needed phase 2 development as there few issues with respect to setup and too much design changes. Created Phase 2 in Sprint 2.
Do's
· Need to clear UI design before development starts.
· Commit after every change rather than commiting all at once especially towards end of sprint
· Team needs to increase development pace.
· Work on better communication between UI and Backend Developers since there were availability issue.
· Team member need to provide at least 4hours time for any communication replies and team member need to reply not more than 4 hours.
Don't
· UI stories timeline not to be under-estimated.
· Need to clear UI design before development starts.
· Be prepared for demos and check issues before demo.
Standup 1 (02/28):
Completion of all Requirement Stories.
Few requirements related doubt cleared.
Commencement Sales Module Development
Discussion on API and UI Screen parameters
Commencement of DB Setup
Standup 2 (03/05):
Cloud DB configuration complete in AWS
Clarified on UI Design for Sales Onboarding page and as Team discussed few changes required.

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
EPIC-3 | Sales Service API
S5-63 | Sales: Onboarding Customer Page -2 | vv | To Do | 100 | 16
S5-70 | Create HTML design | vv | To Do
S5-71 | Update SCSS File | vv | To Do
S5-73 | Adding Validation for all fields in homepage | vv | To Do
S5-72 | Dev Testing Homepage | vv | To Do
S5-64 | Sales: Agreement View Page | mm | To Do | 100 | 16
S5-74 | Create agreement view page | mm | To Do
S5-75 | Add Validations to Agreement View Page | mm | To Do
S5-76 | Dev Test Agreement View Page | mm | To Do
S5-29 | Sales: Customer onboarding API | ds | To Do | 150 | 16
S5-89 | Customer Onboarding API Creation | ds | To Do
S5-90 | Dev Test Customer Onboarding API | ds | To Do
S5-69 | Sales: Agreement view API | vs | To Do | 150 | 16
S5-91 | Create Sales Agreement View API | vs | To Do
S5-92 | Dev Test Sales Agreement View API | vs | To Do
EPIC-4 | Database Config and Integration
S5-38 | Create Database design | pc | To Do | 100 | 16
S5-49 | Create a database architecture and entity diagram | pc | To Do
S5-39 | Create Database Schema and tables | pc | To Do | 40 | 16
S5-47 | Create multiple database schemas to organize your database objects based on their functionality, security requirements, or user access. | pc | To Do
S5-48 | Assign appropriate permissions to the database users to access the required schemas. | pc | To Do
EPIC-4 | DevOps Server Configuration
S5-77 | Configure Jenkins/AWS CI/CD | pc | To Do | 100 | 24
S5-80 | Configure Jenkins in EC2 instance | pc | To Do
S5-81 | Configure Automated Build and store artifact in git repo | pc | To Do
S5-82 | Configure automated deploy in Jenkins | pc | To Do
S5-83 | Monitoring: Enroll team members to receive build and deploy notification | pc | To Do
S5-93 | Integration Test Service APIS | pc | To Do
|  |  |  | 740 | 120 | 0 | 0

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
EPIC-3 | End Customer Service API |  | To Do
S5-16 | End-Customer: Create REST API Framework using Swagger | ds | To Do | 14 | 16
S5-56 | Customer Agreement view API | ds | To Do
S5-57 | Customer Agreement Confirmation API | mm | To Do
S5-58 | Customer Work Tracking API | pc | To Do

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
EPIC-1 | Project Planning and Set Objectives and Design flow
S5-1 | Develop a Project Plan | As a Scrum Master, I want to plan what to do and understand the Solar Project Management tool, so that I can ensure the successful development and implementation of the prototype.
EPIC-2 | Requirement Analysis
S5-12 | Requirement and Fuctionality Analysis for Sales Module | As a requirement engineer, I want to identify the key features and functionalities required to manage sales leads and proposals effectively and specify the data and analytics required to track sales performance and generate sales reports, so that I can develop a prototype that meets their needs and expectations.
S5-13 | Requirement and Fuctionality Analysis for Construction Module | As a requirement engineer, I want to identify the key features and functionalities required to manage project timelines, tasks, and expenses. Specify the data and analytics involved, so that I can develop a prototype that meets their needs and expectations.
S5-14 | Requirement and Fuctionality Analysis for Operation Module | As a requirement engineer, I want to identify the key features and functionalities required to monitor project progress and operational parameters. Specify the data and analytics involved, so that I can develop a prototype that meets their needs and expectations.
S5-15 | Requirement and Fuctionality Analysis for End-Customer Module | As a requirement engineer, I want to identify the key features and functionalities required to track project status and timelines. Specify the data and analytics involved, so that I can develop a prototype that meets their needs and expectations.
S5-16 | Requirement and Fuctionality Analysis for Rule Engine | As a requirement engineer, I want to identify the key features and functionalities required between each stakeholder which will include maker-checker rules, inter-relationships between stakeholders, and the impact of transition. Specify the data and analytics involved, so that I can develop a prototype that meets their needs and expectations.
EPIC-4 | Database Config and Integration
S5-36 | Create and Configure Database connection | As a developer, I want to be able to establish a connection to the database so that I can interact with the data.
S5-37 | Database Hosting in AWS | As an IT administrator, I want to be able to monitor and manage the database resources and usage so that I can ensure the availability and reliability of the system.
S5-38 | Create Database design | As a database developer, I want to create Database design with all schemas and tables with their relationship mapping so that this design architecture can be used to create schemas and tables for the design
S5-39 | Create Database Schema and tables | As a developer, I want to be able to create multiple schemas so that I can organize the data in a logical and meaningful way.
EPIC-3 | Sales Service API
S5-50 | Sales: Create REST API Framework using Swagger | As a developer, create a REST API Frame for Sales Service APIS so that structure can be used to create service logic over it
S5-59 | Sales UI Design and project Setup | As a UI Designer, create a User Interface for the sales section of the application, which represents user interactions with the application.
S5-61 | Sales: Onboarding Customer - Page 1 | As a developer, I want to create a customer onboarding API so that customer can be onboarded when customer onboarding screen hit the api.
S5-65 | Sales: Set Dependencies and initial project setup | As a developer, setup initial project and dependencies so that service API can be built on that frame structure
S5-63 | Sales: Onboarding Customer Page -2 | As a developer, I want to create a customer onboarding API so that customer can be onboarded when customer onboarding screen hit the api.
S5-64 | Sales: Agreement View Page | As a developer, I want to create a sales agreement API so that sales person can generate sales agreement and view when the request is hit.
S5-29 | Sales: Customer onboarding API | As a UI Designer, I want to create a visually appealing homepage that provides easy access to all the key features of the website, so that users can navigate the site with ease.
S5-69 | Sales: Agreement view API | As a UI Designer, I want to create an intuitive search feature that allows users to quickly find what they are looking for, so that they can save time and have a positive user experience.
EPIC-3 | End Customer Service API
S5-16 | End-Customer: Create REST API Framework using Swagger | As a developer, create a REST API Frame for End Customer Service APIS so that structure can be used to create service logic over it
EPIC-4 | DevOps Server Configuration
S5-77 | Configure Jenkins/AWS CI/CD | As a DevOps Engineer, setup Jenkins CI/CD Environment so that the application build and deploy can be automated.
S5-79 | Setup AWS EC2 instance for Sales Service | As a DevOps Engineer. I want to set AWS EC2 instance for sales service so that Jenkins can deploy the sales services directly on cloud AWS server.

## Testing cases
Testing ID | Testing Name | Testing Description