## Team
Initials | First | Last | Email | GitHub Username | ScrumMaster
pc | Prateek Singh | Chauhan | pchauha2@stevens.edu | sabudanakichdi | Yes
mm | Monica | Monica Mallamputti | mmallamp@stevens.edu | Monicaprojects21 | No
vm | Vishnu | Mandula | vmandula@stevens.edu | Vishnu1604 | No
ds | Diya | Sanghvi | dsanghv1@stevens.edu | Diya1201 | No
vs | Vikas Singh | Vyaqti | vsingh22@stevens.edu | VyaqtiVikasSingh | No
|  |  | GitHub Repository: | https://github.com/sabudanakichdi/ssw555_agile_project

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | S5-1 | Develop a Project Plan | pc | Done
1 | S5-8 | Requirement and Fuctionality Analysis for Sales Module | vs | In Progress
1 | S5-8 | Requirement and Fuctionality Analysis for Construction Module | vv | In Progress
1 | S5-8 | Requirement and Fuctionality Analysis for Operation Module | mm | In Progress
1 | S5-8 | Requirement and Fuctionality Analysis for End-Customer Module | ds | In Progress
1 | S5-8 | Requirement and Fuctionality Analysis for Rule Engine | pc | To Do

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2022-06-06 | 24 |  | 0
Sprint 1 | 2022-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2022-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2022-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2022-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2022-02-23 | 36 |  | 0
2023-03-09 | 30 | 6 | 250 | 120 | 125

## Sprint1
Story ID | Story Name | Owner | Status | Est Size (Story Points) | Est Time (In hours) | Act Size | Act Time | Completed
EPIC-1 | Project Planning and Set Objectives and Design flow
S5-1 | Develop a Project Plan | pc | Done | 5 | 8 | 5 | 7 | 2023-02-18
S5-2 | Identify and understand the problem statement for given solar management tool | pc | Done |  |  |  |  | 2023-02-16
S5-4 | Identify and understand the problem statement for given solar management tool | ds | Done |  |  |  |  | 2023-02-17
S5-5 | Identify and understand the problem statement for given solar management tool | vs | Done |  |  |  |  | 2023-02-18
S5-6 | Identify and understand the problem statement for given solar management tool | mm | Done |  |  |  |  | 2023-02-18
S5-7 | Identify and understand the problem statement for given solar management tool | vv | Done |  |  |  |  | 2023-02-18
EPIC-2 | Requirement Analysis
S5-8 | Requirement and Fuctionality Analysis for Sales Module | vs | In Progress | 2 | 8
S5-10 | Identify the key features and functionalities | vs | In Progress
S5-11 | Identity the specific data and analytics required for dashboard | vs | To Do
S5-12 | Create a Requirement analysis report | vs | To Do
S5-13 | Requirement and Fuctionality Analysis for Contruction Module | vv | In Progress | 2 | 8
S5-17 | Identify the key features and functionalities | vv | In Progress
S5-21 | Identity the specific data and analytics required for dashboard | vv | To Do
S5-25 | Create a Requirement analysis report | vv | To Do
S5-14 | Requirement and Fuctionality Analysis for Operations Module | mm | Done | 2 | 8 | 2 | 8 | 2023-02-20
S5-18 | Identify the key features and functionalities | mm | Done
S5-22 | Identity the specific data and analytics required for dashboard | mm | Done
S5-26 | Create a Requirement analysis report | mm | Done
S5-15 | Requirement and Fuctionality Analysis for End-User Module | ds | In Progress | 2 | 8
S5-19 | Identify the key features and functionalities | ds | In Progress
S5-23 | Identity the specific data and analytics required for dashboard | ds | To Do
S5-27 | Create a Requirement analysis report | ds | To Do
EPIC-3 | End Customer Service API
S5-16 | End-Customer: Create REST API Framework using Swagger | ds | To Do | 2 | 16
S5-56 | Customer Agreement view API | ds | To Do
S5-57 | Customer Agreement Confirmation API | mm | To Do
S5-58 | Customer Work Tracking API | pc | To Do
EPIC-4 | Database Config and Integration
S5-36 | Create and Configure Database connection | pc | In Progress | 1 | 4
S5-41 | Choose a database management system (DBMS) that suits your project's requirements, such as MySQL, PostgreSQL, or MongoDB. | pc | Done |  |  |  |  | 2023-02-20
S5-42 | Install the database software on your server or local machine. | pc | In Progress
S5-36 | Database Hosting | pc | To Do | 2 | 8
S5-43 | Choose a cloud service provider and Create a new virtual machine instance and assign it resources like CPU, memory, and storage. | pc | To Do
S5-44 | Install the database software on the virtual machine and create a new database instance and assign a name to it. | pc | To Do
S5-45 | Create a new user account for the database with appropriate privileges. | pc | To Do
S5-46 | Open the necessary network ports to allow external access to the database. | pc | To Do
EPIC-3 | Sales Service API
S5-50 | Sales: Create REST API Framework using Swagger | ds | To Do | 2 | 16
S5-53 | Sales Agreement view API | ds | To Do
S5-55 | Sales agreement Confirmation API | vv | To Do
S5-54 | Sales Agreement Generate API | mm | To Do
S5-52 | Sales Customer Onboarding API | vs | To Do
Review Results
Keep doing:
Review Results
Keep doing:
Bring pizza to our meetings
Bring silverware for everyone
Avoid:
Leaving leftover pizza on the counter

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
EPIC-2 | Requirement Analysis
S5-16 | Requirement and Fuctionality Analysis for Rule Engine | pc | To Do | 2 | 16
S5-20 | Identify the key features and functionalities | pc | To Do
S5-24 | Identity the specific data and analytics required for dashboard | pc | To Do
S5-28 | Create a Requirement analysis report | pc | To Do

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01
US02
US03
US04
US05
US06
US07
US08
US09
US10
US11
US12
US13
US14
US15
US16
US17
US18
US19
US20
US21
US22
US23
US24
US25
US26
US27
US28
US29
US30
US31
US32
US33
US34
US35
US36
US37
US38
US39
US40
US41
US42

## Testing cases
Testing ID | Testing Name | Testing Description